Comments-Response Matrix Based On SEMR Findings- 05.09.2020

| Sr. No | Comments | Response |
| --- | --- | --- |
| 1 | In Para 2 it is written that “WBDWSIP will be implemented over years between 2018 and 2024” - Please check and confirm that construction period is 3 years from date of issue of work order and O &M is 2 years thereafter | Overall project WBDWSIP implementation from 2018 to 2024.i.e 6 years For each package implementation period 3 years after date of issue of work order and O & M of 2 years after construction. Mentioned in the report |
| 2 | Table 3: Status of Implementation of Sub project (30th April 2020) - Please mention date of package wise closure/suspension of site construction activities due to COVID 19 pandemic situation in this present SEMR. Similarly in the next SEMR mention package wise date of resumption of site activities after complying with all guidelines /protocols of COVID 19 management as per SOP prepared by PMU for prevention and risk minimization of corona virus disease (covid-19) at the facilities and work sites of WBDWSIP. - Attach package wise/district wise photographs/display board/notice for suspension of work due to COVID 19 pandemic | Due to sudden declaration of total lockdown contractor unable to take photograph just before lockdown due to COVID 19 Notice of suspension – total lockdown issued by Govt. of West Bengal shown below the Table. Resumption of work will be as per Govt. order and protocol of COVID 19 management as per SOP of the project. |
| 3 | There are 2 small packages as grant from the Japan Fund for Poverty Reduction (JFPR): (i) SAN/01: Pilot Faecal Sludge and Septage Management Plant and (ii) STWM/01 (Smart Water Management: Gram Panchayat level smart water management equipment) . Package SAN/01 has been awarded --- As suggested in 1st SEMR. IEE/due diligence report to be prepared once location is finalized. Please update the status accordingly and give a time line for preparation and submission of reports. | Till report period package SAN/01 has been awarded. Study location of the said package is not yet finalized. Preparation of IEE will be done after selection of project construction locations and finalization of scope. Mention in para 12 |
| 4 | Be consistent with spelling of Location/district/ block names (eg. Medinipur is written differently in many places) | Done |
| 5 | Table 3A : Zone-wise Submitted SEMP Status for North 24 Parganas, Bankura and East Medinipur Packages - Submit pending SEMPs as per the table to ADB for information / concurrence before start of work. - Please upload all the approved SEMPs and updated IEEs for this current report period (November 2019 to April 2020) in WBDWSIP website and give a web-link in Table 3A for quick reference. | Submission list shown in Table 3A. Uploading done in project website and link provided. Further project MIS system development undergoing. All reports including SEMPs will be uploaded on that platform after approval of PMU Work at specific zone started after approval of SEMP. |
| 6 | Package BK/03- Tree felling is required for construction of WTP. - Application send to DFO, Forest dept. Permission obtained on 05.12.2019 for felling of 232 mos. - Please clarify status of felling of 232 trees and compensatory plantation as permission was obtained on 5th December 2019 and valid upto 18.03.2020. - Why renewal is necessary again? | Tree felling was planned before lockdown by Forest Dev. Corporation but delayed due to some administrative issue, however sudden declaration of the complete lockdown it was not possible, meanwhile validity of the permission expired. Already applied for renewal of the same. After receive of renewed NOC and decision of Forest Dev. Corporation tree felling will be done. Mentioned in Table 4. |
| 7 | Table 8: Details of Contractor’s safeguard officer for WBDWSIP - Please note that Contractor should mobilise dedicated EHS officer in all packages for smooth implementation of EMP.PMC/ DSC to look into this matter - It appears from the table that same person is responsible for BK/04 and EM/02, which is not acceptable. | EHS officer will be mobilize for the package EM/01 before start of construction activity. Typographical error. EHS officer of BK/04 and EM/02 are separate. Changes done in table 8 |
| 8 | Table 14: Overall Compliance with Environmental Management Plan - What is the status of identification and establishment of labour camps in package EM O2. In the submitted SEMPs it is mentioned that labour camps will be identified/constructed. | Only the pre-construction activities ongoing. Labour camp has been proposed at Monoharpur. Construction of labour camp not yet started |
| 9 | Para 58 : Details of complaints received during report period and resolved status attached as Appendix 16. - Please provide in the Main report package wise summarized details of complaints received, Nature of complaints, whether issues are resolved or not, time taken to resolve complaints. | Summary included in Table 15 below para 58. Details shown in Appendix. Till period no complaints received for Bankura packages |
| 10 | In the Main volume (also in Appendix) - Give a summary of Package wise details of consultations/FGDs conducted in tabular form - Give a summary of Package wise details of Training, Workshops, Seminars conducted during the reporting period - Provide package wise break up of no of participants in consultations/ FGDs the for quick reference. - Provide package wise actual numbers of female participants in all training /workshops/seminars/FGDs along with percentage. | Details are shown in Table 17A to 17D in Main text Appendix shown sample FGD/ consultation |
| 11 | It is observed that In some packages No of samplings are not according to EMP provision – If sites and alignment are finalized monitoring for pre-construction period to be completed immediately after monsoon period in all packages and number of samplings would be according to EMP. | Pre- construction phase monitoring completed for all packages as per provision of Monitoring Plan, except for package N 24 pgs/01. After possession of GLSRs site and after monsoon season monitoring will be done. Mention below Table 21A |
| 12 | Figure 12 & 13 : Graphical presentation of Air quality and Noise Level data for Bankura Packages are to be compared with respective NAAQS . | Graphical presentation and comparison done and shown in Figures 12A- 12D |
| 13 | Package EM 02: Show and compare the findings of analytical results graphically with NAAQS. | Shown in Figures below Table 45 |
| 14 | Appendix 12: Sample Accident/First Aid Report: Sample reports/records attached for North 24 Pgs packages are illegible. Please provide summarised information in tabular format in accordance to Taldangra record of accidents attached in Appendix 12. | Attached as per suggestion |